## Folha1
Sprint Burndown Chart
Task Number | Task | Initial Estimate | 2021-11-29 | 2021-11-30 | 2021-12-01 | 2021-12-02 | 2021-12-03 | 2021-12-04 | 2021-12-05 | 2021-12-06
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8
20 | Design pattern in DatabaseChangeMonitor.java | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0
21 | Design pattern in ViewModelTableRowFactory.java | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0
22 | Design pattern in DirectoryDialogConfiguration.java | 3 | 0 | 2 | 0 | 0 | 0 | 0 | 1 | 0
23 | Code smell in RisImporter.java | 3 | 0 | 0 | 2 | 0 | 0 | 0 | 1 | 0
24 | Code smell in BibtexCaseChanger.java | 3 | 0 | 0 | 2 | 0 | 0 | 0 | 1 | 0
25 | Code smell in ComplexSearchQuery.java | 3 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0
27 | Use Case Diagram (added the 'Using PDFs') | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
30 | Use Case Descriptions | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0
31 | Use Case Diagram (added the base diagram and"Manually, With ID") | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
32 | Use Case Diagram (added the "Reference tex, Using Online Service" | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
33 | Lines of Code Metrics doc | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0
34 | Lines of Code Metrics data xls | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
35 | Metrics MOOD (package groups and auximport) | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0
36 | Data collected (metrics) | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0
37 | Code Smell Long method | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0
38 | Code Smell Large class | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
39 | Martin packagin metrics | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0
Remaining Effort |  | 42 | 39 | 36 | 32 | 30 | 30 | 24 | 3 | 0
Ideal Trend |  | 42 | 36.75 | 31.5 | 26.25 | 21 | 15.75 | 10.5 | 5.25 | 0